## Sheet1
Exhibit 4 - Microwave AT Format
| Project Category | For Sites ID (RAN Site ID) | MIDS Plan ID (LB ID)
| NEW DEPLOYMENT XPIC | MPRA22 | MW-N-HP-13062023-8222
Product Name | ERICSSON |  |  | Date :
The responsibilities specified shall apply as from MSP if not otherwise stated.
The ambit of this ATP is to specify ATP for MW Link Network Performance, or as may be amended or added to in accordance with Mutual Agreement.
Unless agreed otherwise, all amendments to this ATP must be recorded in writing and implemented in accordance with the agreement.
Site Details : | Planned Site A | Actual Site A | Planned Site B | Actual Site B | Additional Remarks :
Site ID | MPRA23 | MPRA23 | MPRA22 | MPRA22
Site Name | FFFF | FFFF | FFFF | FFFF
Site Address | FFFF | FFFF | FFFF | FFFF
Site Type (Indoor/Outdoor/IBS) | FFFF | FFFF | FFFF | FFFF
Locator ID | FFFF | FFFF | FFFF | FFFF
TOCO(Indus,Infratel.GTL,Bharti Owned) | INDUS | INDUS | INDUS | INDUS
ToCo Site ID | IN-1249971 | IN-1249971 | IN-3208426 | IN-3208426
Site Lat/Long | 76.99737/29.39352 | 76.99737/29.39352 | 76.9933/29.40382 | 76.9933/29.40382
Azimuth to other site | 339.93 | 339.93 | 159.93 | 159.93
Tower Height | FFFF | FFFF | FFFF | FFFF
Antenna Size (0.3, 0.6, 0.9, 1.2, 1.8 Mtrs) | 0.6 | 0.6 | 0.6 | 0.6
Antenna Height (AGL- meters ) | 40 | 40 | 30 | 30
Antenna Polarization (Horizontal / Vertical) (As per planning guidelines) | H+V | H+V | H+V | H+V
No. of Strut Rods installed (0/1/2) for 1.2/ 1.8 mtr antennas (1.8M-2 Rods,1.2M- 1 Rod is mandatory) | 1
Path Length (kms) | 1.21 | 1.21 | 1.21 | 1.21
FM Engg Name | FFFF | FFFF | FFFF | FFFF
Zone | FFFF | FFFF | FFFF | FFFF
Remarks | FFFF | FFFF | FFFF | FFFF
Functional Test/Commissioning and Acceptance
Type of Equipment (MLE/MLTN,HC,FHY,FHO,Ceragon,NEC,Huawei,DragonWave Etc.) | ERICSSON | ERICSSON | ERICSSON | ERICSSON
TDM Link Capacity (4E1,16E1,32E1,75E1 Etc.) | 1.4 | 5 | 1111 | 0.5
Ethernet Link Capacity (Mbps Etc.) | PPPPP | PPPPP | PPPPP | PPPPP
Software Version IDU (latest available version) | PPPPP | PPPPP | PPPPP | PPPPP
Software Version ODU(latest available version) | PPPPP | PPPPP | PPPPP | PPPPP
IDU/Magazine (New/Existing) | PPPPP | PPPPP | PPPPP | PPPPP
System Configuration(PDH/ SDH/ Hybrid/ Packet) | PPPPP | PPPPP | PPPPP | PPPPP
Link configuration (1+0/1+1/2+0/XPIC/1G) | 1+0 | 1+0 | 1+0 | 1+0
Switch card redundancy (Y/N/NA) | yes | NO | Yes | Yes
Optical card redundancy (Y/N/NA) | yes | NO | Yes | Yes
Power card redundancy (Y/N/NA) | yes | NO | Yes | Yes
IDU Model | PPPPP | PPPPP | PPPPP | PPPPP
Sl. No. of IDU | PPPPP | PPPPP | PPPPP | PPPPP
ODU Model | PPPPP | PPPPP | PPPPP | PPPPP
Sl. No. of ODU | PPPPP | PPPPP | PPPPP | PPPPP
Power Supply to ODU through PoE or direct | PPPPP | PPPPP | PPPPP | PPPPP
External Power Injector (Y/N/NA) | yes | NO | Yes | Yes
Type of external Power Injector (2/4/8 port, Indoor/outdoor) | PPPPP | PPPPP | PPPPP | PPPPP
Number of outdoor weatherproof CAT-6 cables | PPPPP | PPPPP | PPPPP | PPPPP
Outdoor weatherproof CAT-6 cables are armoured (Y/N/NA) | yes | NO | Yes | Yes
Unused ODU ports are weatherproof capped (Y/N/NA) | yes | NO | Yes | Yes
Protection Conduit for Patch Cords Interconnections, OD power cable and E1 cable routing between 2 shelters or 2 different Cabinets. | PPPPP | PPPPP | PPPPP | PPPPP
Card type in IDU | PPPPP | PPPPP | PPPPP | PPPPP
IP20S/IP20C | PPPPP | PPPPP | PPPPP | PPPPP
Frequency Tx (MHz) | 15243 | PPPPP | 14823
Frequency Rx (MHz) | 14823 | PPPPP | 15243
Tx Power (dBm) | 8 | PPPPP | 8
RSL(dBM) (<=2 dB Deviation permitted)* | -35.14 | PPPPP | -35.14
Modulation | 1024QAM | PPPPP
Fade Margin | 23.62 | PPPPP | 23.62
ATPC Enabled? (Y/N/NA) | No | NO | No | Yes
ACM Enabled (Y/N/NA) |  | NO |  | Yes
Hi Lo Violation (Y/N/NA) (No violation accepted) | yes | NO | Yes | Yes
RSL at near End when Far End Tx Power Mute (Pl note value) | PPPPP | PPPPP | PPPPP | PPPPP
HOP visible in NMS (Y/N/NA)(NMS Visibility is Mandatory) | yes | NO | Yes | Yes
HOP ID (standard nomenclature to be configured in NMS also) | MPRA23-MPRA22 | MPRA23-MPRA22 | MPRA22-MPRA23 | MPRA22-MPRA23
IP Address/Subnet Mask | PPPPP | PPPPP | PPPPP | PPPPP
Link is alarm free (Y/N/NA) (No Alarm accepeted Mandatory) | yes | NO | Yes | Yes
External Alarms extended for Outdooor cabinets
Management IP address (if applicable) | PPPPP | PPPPP | PPPPP | PPPPP
Management VLAN ID (for DCN) | PPPPP | PPPPP | PPPPP | PPPPP
Conflict in Management & Traffic VLAN (Y/N/NA) | NO | NO | nO | yEs | Please Enter Correct Conflict in Management Status!!!
Unused VLAn configured in IDU (Y/N/NA) | NO | NO | nO | yEs | Please Enter Correct Unsed Vlan Configured in IDU Status!!!
Broadcast Limit configured on all Ethernet Ports (Y/N/NA) | NO | NO | nO | yEs | Please Enter Correct Broadcast Limit Configured Status!!!
All configured VLANs belongs to only one Fiber POP (Y/N/NA) | NO | NO | nO | yEs | Please Enter Correct All Configured Vlan Status!!!
Management of connecting 3rd party MW equipment | PPPPP | PPPPP | PPPPP | PPPPP | Please Enter Correct QoS COnfigured Status!!!
Number of Ethernet ports used for traffic | PPPPP | PPPPP | PPPPP | PPPPP | Please Enter Correct LoopBack Status!!!
QoS configured (Y/N/NA) (As per planning Instruction) | NO | NO | nO | yEs | Please Enter Correct All Ethernet config as pe planning instruction (Y/N/NA) !!!
Loopback (RF, IF, NW) testing done (Y/N/NA) | NO | NO | nO | yEs | Please Enter Correct All TDM config as pe planning instruction (Y/N) !!!
All Ethernet config as pe planning instruction (Y/N/NA) | NO | NO | nO | yEs | Please Enter Correct BH E1 till HO Point in ring protection((Y/N/NA))!!!
All TDM config as pe planning instruction (Y/N/NA) | NO | NO | nO | yEs | Please Enter Correct Ring testing(in case of ring) - SNCP/ ERPS Switching (OK/ NOT OK/ NA)!!!
Ethernet throughput (in Mbps) | PPPPP | PPPPP | PPPPP | PPPPP | Please Enter Correct Auto Switching of traffic (Incase of TN/SDH Hop-Ring) (OK/not OK/NA)!!!
Optical receive level at optical IF ports | PPPPP | PPPPP | PPPPP | PPPPP
Clock Synchronization define (Y/N/NA)(As per planning Instruction) | NO | NO | nO | yEs
Latency (End to end path)- Ring/ Chain | PPPPP | PPPPP | PPPPP | PPPPP
Packet Drop (End to end path)- Ring/ Chain | PPPPP | PPPPP | PPPPP | PPPPP
BH E1 till HO Point in ring protection((Y/N/NA)) (Deviation to be captured separately) | NO | NO | nO | yEs
Ring testing(in case of ring) - SNCP/ ERPS Switching (OK/ NOT OK/NA) | NOT ok | NOT ok | nA | Ok
Auto Switching of traffic (Incase of TN/SDH Hop-Ring) (OK/not OK/NA) (forceful switching testing mandatory) | NOT ok | NOT ok | nA | Ok
Remarks | PPPPP | PPPPP | PPPPP | PPPPP
Installation Checklist
Tx rack is fastened to floor & is clean.(No Shaking & dust free) | NO | NO | nO | yEs | Please Enter Correct Tx Rack Fastened Status!!!
MW/ Tx rack DDU/ DCDB / Tx equipments supply from critical LVD | NO | NO | nO | yEs | Please Enter Correct Tx Equipment Supply Status!!!
Verify all MCBs on DDU/ DCDB/ SMPS are labelled (Legible labelling) | NO | NO | nO | yEs | Please Enter Correct Verify All MCBs Status!!!
Position of IDU magazine (Tx rack,BTS,wall mount) | NO | NO | nO | yEs | Please Enter Correct Position of IDU Magazine Status!!!
IDU & Magazine installaton(nuts tighten & cards jacked completely in slots) |  |  | nO | yEs | Please Enter Correct Idu And Magazine Installation Status!!!
Labelling of IF cable at Both End,ODU,IDU,Power cable,Ethernet cables,PCM ( E1) cable,DDF,MCB etc is verified.(Legible labelling) | sfefe | sfefe | sfefe | sfefe | any value accepted for now
Check All cables are routed inside the Tx rack (Ethernet cables,E1 cables,power cable,earthing cable etc) (No loose hanging) | NO | NO | nO | yEs | any value accepted for now
Protection Conduit for Patch Cords ,Interconnections,OD power cable and E1 cable routing between 2 shelters or 2 different Cabinets. | NO | NO | nO | yEs | Please Enter Correct Protection Conduit Status!!!
IF cable/CAT6 routing is secured with IF clamps/Ties on cable tray.
Earthing of Tx rack is present & connected | NO | NO | nO | yEs | Please Enter Correct Earthig for Tx Rack Status!!!
Earthing of Magazine, DDU, IDU, Fan unit & any other TX equipment is present & connected | NO | NO | nO | yEs | Please Enter Correct Earthig Of Magazine Status!!!
IDU Power Cable routing/ Labeling verified (Legible labeling, crimped Lugs & coloured PVC tape used) | NO | NO | nO | yEs | any value accepted for now
IDU Grounding cable connection/ Labeling verified (crimped Lugs/Legible Labelling) | NO | NO | nO | yEs | Please Enter Correct IDU Grounding Cable Status!!!
Earthing from Equipment bus bar of IDU connected (Crimped Lugs) | NO | NO | nO | yEs | any value accepted for now
ODUs are mounted with all nuts & bolt in place and securely tightened | NO | NO | nO | yEs | Please Enter Correct ODUs Are Mounted Status!!!
Verify DDF Rack & Krone Module grounded to the equipment earth | NO | NO | nO | yEs | Please Enter Correct Verify DDF Rack Status!!!
Verify IF connectors/RJ45 are locked while terminated at IDU and ODU | NO | NO | nO | yEs | Please Enter Correct Verify IF connectors Status!!!
Down bent given to IF cable/CAT6 at shelter entry | NO | NO | nO | yEs | Please Enter Correct Down bent given to IF cable Status!!!
At ODU end the 1 Mtrs extra cable loop tightened with tower. | NO | NO | nO | yEs | Please Enter Correct At ODU end the 1 Mtrs extra cable loop tightened with tower Status!!!
At ODU the IF cable/CAT6 should not hang,otherwise it will load ODU N type connector | NO | NO | nO | yEs | Please Enter Correct At ODU the IF cable Status!!!
IF cable/CAT6 length (Mtrs) | NO | NO | nO | yEs | any value accepted for now
Earthing of IF Cable/CAT6 connected to Rack/ EGB | NO | NO | nO | yEs | Please Enter Correct Earthing of IF cable Status!!!
Weather proofing of IF cable/CAT6 at earthing point done | NO | NO | nO | yEs | any value accepted for now
Sealing of IF cable entry point to Shelter & roxtec sealing at entry point to shelter done | NO | NO | nO | yEs | Please Enter Correct Sealing of IF cable entry point to Shelter Status!!!
Antenna Clamps tightened with mounting pole (No loose clamping permitted) | NO | NO | nO | yEs | Please Enter Correct Antenna is tightened with Pole Status!!!
Antenna is tightened with Pole (All nuts & bolts fixing the antenna are tightened) | NO | NO | nO | yEs | Please Enter Correct Antenna Clamps tightened with mounting pole Status!!!
The aligned positions of antenna, fixing clamps, fine alignment rods,vertical alignment rods and strut marked with thin paint lines at multiple places | NO | NO | nO | yEs | Please Enter Correct The aligned positions of antenna Status!!!/
ODU is grounded (Y/N/NA) | NO | NO | nO | yEs | Please Enter Correct ODU is grounded Status!!!
ODU/Antenna is marked with far end Site ID (Y/N/NA) | NO | NO | nO | yEs | Please Enter Correct ODU/Antenna is marked with far end Site ID Status!!!
Weather proofing of IF connector at ODUs (Water should not ingress) | NO | NO | nO | yEs | any value accepted for now
MW Coupler/Strut rods fixing for 1.2,1.8 Mtr MW Antenna as per installation guidelines (90 degree +- 15 degree) | NO | NO | nO | yEs | Please Enter Correct MW Coupler Status!!!
All Dummies Installed (Y/N/NA) | NO | NO | nO | yEs | Please Enter Correct All Dummies Installed Status!!!
Fan units installed & working for magzine for all types of equipments | NO | NO | nO | yEs | Please Enter Correct Fan units installed Status!!!
Power Backup Available (Y/N/NA) (pl note no of hrs of backup) | NO | NO | nO | yEs | Please Enter Correct Power Backup Available Status!!!
Verify IDU Connected with Dual Power Source | NO | NO | nO | yEs | Please Enter Correct IDU Connected with Dual Power Source Status!!!
Grounding of Mast | NO | NO | nO | yEs | Please Enter Correct Grounding of Mast Status!!!
Lightening arrestor Installed. | NO | NO | nO | yEs | Please Enter Correct Lightening arrestor Installed Status!!!
Grounding of Lightening arrestor | NO | NO | nO | yEs | Please Enter Correct Grounding of Lightening arrestor Status!!!
SACFA ID (Note Online ID) | PPPPP | PPPPP | PPPPP | PPPPP
All Nuts & Bolts used are as per specification & recommendations only | NO | NO | nO | yEs | any value accepted for now
All the deviation (if any) must be captured separately in Deviation format and to be approved by Circle CTO only | NO | NO | nO | yEs | any value accepted for now
Remarks | PPPPP | PPPPP | PPPPP | PPPPP
Stability Test: Statistics During 24 Hrs Test (On Need basis)
Result of 24 hrs. BER Test Acceptance (Y/N/NA) | NO | NO | nO | yEs | Please Enter Correct Result of 24 hrs. BER Test Acceptance (Y/N/NA)
TT(Total Time) | PPPPP | PPPPP | PPPPP | PPPPP
AT(Available Time) | PPPPP | PPPPP | PPPPP | PPPPP
ES(Error Secods) | PPPPP | PPPPP | PPPPP | PPPPP
BBE (Background BER) | PPPPP | PPPPP | PPPPP | PPPPP
SES(Severly Error Seconds) | PPPPP | PPPPP | PPPPP | PPPPP
EB(Error block) | PPPPP | PPPPP | PPPPP | PPPPP
Test to be error free | PPPPP | PPPPP | PPPPP | PPPPP
Site Layout Diagram Enclosed | PPPPP | PPPPP | PPPPP | PPPPP
MW BOQ sheet attached with wiring diagram & attached to MW Rack | PPPPP | PPPPP | PPPPP | PPPPP
Planning Design data sheet attached | PPPPP | PPPPP | PPPPP | PPPPP
Site Photograph for MW Ant, Cabling and Eqpt Attached | PPPPP | PPPPP | PPPPP | PPPPP
Signoff : | PPPPP | PPPPP | PPPPP | PPPPP
Project Engineer Name & Sign ( MS Partner) | PPPPP
Engg FM Name & Sign ( MS Partner) | rgrgrg |  | OPS SPOC Name & Sign (Bharti) | grggrrg
Project Manager Name & Sign (Bharti) | grggrgr |  | Project Manager Name & Sign (SP) | rgrrgrg
Mobile Number | grgrgrgrgrg |  | Mobile Number | grgrgrgrgrgr