## Sheet0
Planning Input |  |  | System Generated | Planning Input | [16 empty] | Partner Site Detail | [34 empty] | Deployment Team Input |  |  |  |  | System Generated |  | Partner Input | System Generated | Partner Input | System Generated | Partner Input | System Generated | Partner Input | System Generated | Partner Input | System Generated | Partner Input |  |  | Hop Dismantle Status - System Generated |  | System Generated |  |  |  |  | Partner Input
Circle | SCOPE ADD DATE | Plan Release Date For Ts | Plan Id | Sorted link(A/B) | HOP TECHNOLOGY | PROJECT | LINK ID(A-B) | Link ID(B-A) | SITE ID | Link Type | Modules Name | Modules Qty | Modules-Serial No | Modules Type | Hop Make | HOPE TYPE | Product Name | Frequency Band | Site IP | Slot Number | Unique Plan ID | Unique Site ID | Locator ID | Dismantling Partner Name | Work Allocation date | Survey Date-DD-MM-YYYY | Survey-Modules Name | Survey-Module Qty | Survey-Module Serial No | Survey-missing Remark | Circle Approved QTY | SREQ/CREQ/REQ Number | SREQ/CREQ/REQ Date-DD-MM-YYYY | Dismantling Date-DD-MM-YYYY | Dismantled-Modules Name | Dismantled-Module Qty | Dismantled-Module-Serial No | Item code | DC Request Date | DC NUMBER | Vehicle Need Date -DD-MM-YYYY | Vehicle Requested Date | Vehicle Reported Date | Pick Date | Pick/Ship QTY | Ship Date | PICK/SHIP Status | WH/CAM Submission Date-DD-MM-YYYY | WH/CAM Submission Qty | OCI Date-DD-MM-YYYY | OCI QTY | Physical Ok/Not Ok | Final SRN Status (Complete/Pending/WIP) | SREQ Status | Rejected | Antenna Deloading SR Date | Antenna Deloading SR Number | TOCO Name | TOCO ID | Remarks | Deloading Serial No | GAP B/w Plan vs Survey Module Count | Plan vs Survey Gap Reason | GAP B/w Survey Module Count VS Circle Approved count | Survey vs Circle Approval Gap Reason | GAP B/w Circle Approved count Vs Dismantled Module Count | Circle Approved vs Dismantled Gap Reason | GAP B/w Dismantled Vs WH Submission Module Count | Dismantled vs WH Submission Gap Reason | GAP B/w WH Vs OCI Module Count | WH vs OCI Gap Reason | GAP B/w Planning Approved QTY Vs WH OCI Module Count | Planning vs OCI Gap Reason | Remarks Reason | Stage Completion Remark for I&C Partner | HOP DISMANTLE STATUS | HOP DISMANTLE CATEGORY | Plan Release to TS Ageing | TS to Partner Assignment Ageing | Partner Assignment to Material Dismantle Done | Dismantle Done to NMS Deletion Ageing | Partner Assignment to Deloading SR Completed/NMS Deletion Ageing | TS Remark | Missing Remark | Running Remark | IM | SRN Type(SREQ/REQ/CREQ)
AP | 2025-09-12 |  | MW-D-AP-12092025-9490 | NDL005/NDL027 | MW | From POP_Tree | NDL005-NDL027 | NDL027-NDL005 | NDL005 | XPIC | 0.6 | 1 | NA7955 | ANTENNA | Ericsson | Split | NA | 15Ghz | 0.0.0.0 | NA | AP_NDL005-NDL027_Ericsson_AMM 20P_Split_15Ghz¦AP¦NDL005-NDL027¦NDL005¦ANTENNA¦NA7955 | AP_NDL005 | 123 | Vedangcellular | 2025-12-11 |  | NA | 0 |  | INVALID | 0 | INVALID | [22 empty] | NO |  |  | INDUS | IN-1043179 |  |  | 1 |  | 0 |  | 0 |  | 0 |  | 0 |  | 1 |  | Material not found during in survey | Material not found during in survey | Pending |  | 73 | 16 | 0 | 0 | 0
AP | 2025-09-12 |  | MW-D-AP-12092025-9490 | NDL005/NDL027 | MW | From POP_Tree | NDL005-NDL027 | NDL027-NDL005 | NDL005 | XPIC | 6363 | 1 | CR9K727578 | ODU | Ericsson | Split | AMM 20P | 15Ghz | 0.0.0.0 | FRLT 1/18/1 | AP_NDL005-NDL027_Ericsson_AMM 20P_Split_15Ghz¦AP¦NDL005-NDL027¦NDL005¦ODU¦CR9K727578 | AP_NDL005 | 123 | Vedangcellular | 2025-12-11 | 2025-11-17 |  | 0 |  | INVALID | 0 | REQ | [22 empty] | NO |  |  | INDUS | IN-1043179 |  |  | 1 |  | 0 |  | 0 |  | 0 |  | 0 |  | 1 |  | Material not found during in survey | Material not found during in survey | Pending |  | 73 | 16 | 0 | 0 | 0
AP | 2025-09-12 |  | MW-D-AP-12092025-9490 | NDL005/NDL027 | MW | From POP_Tree | NDL005-NDL027 | NDL027-NDL005 | NDL005 | XPIC | NA | 0 | NA | IDU | Ericsson | Split |  | 15Ghz |  |  | AP_NDL005-NDL027_Ericsson_AMM 20P_Split_15Ghz¦AP¦NDL005-NDL027¦NDL005¦IDU¦NA | AP_NDL005 | 123 | Vedangcellular | 2025-12-11 | 2025-11-17 | NA | 0 |  | INVALID | 0 | CREQ | [22 empty] | NO |  |  | INDUS | IN-1043179 |  |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | Material not found during in survey | Material not found during in survey | Pending |  | 73 | 16 | 0 | 0 | 0
AP | 2025-09-12 |  | MW-D-AP-12092025-9490 | NDL005/NDL027 | MW | From POP_Tree | NDL005-NDL027 | NDL027-NDL005 | NDL005 | XPIC | NA | 0 | NA | MDU | Ericsson | Split |  | 15Ghz |  |  | AP_NDL005-NDL027_Ericsson_AMM 20P_Split_15Ghz¦AP¦NDL005-NDL027¦NDL005¦MDU¦NA | AP_NDL005 | INVALID | Vedangcellular | 2025-12-11 | 2025-11-17 | NA | 0 |  | INVALID | 0 |  | 2026-02-26 | [21 empty] | NO |  |  | INDUS | IN-1043179 |  |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | Material not found during in survey | Material not found during in survey | Pending |  | 73 | 16 | 0 | 0 | 0
AP | 2025-09-12 |  | MW-D-AP-12092025-9490 | NDL005/NDL027 | MW | From POP_Tree | NDL005-NDL027 | NDL027-NDL005 | NDL005 | XPIC | 6363 | 1 | CR9K813887 | ODU | Ericsson | Split | AMM 20P | 15Ghz | 0.0.0.0 | FRLT 1/19/1 | AP_NDL005-NDL027_Ericsson_AMM 20P_Split_15Ghz¦AP¦NDL005-NDL027¦NDL005¦ODU¦CR9K813887 | AP_NDL005 | 123 | Vedangcellular | 2025-12-11 | 2025-11-17 | NA | 0 |  | INVALID | 0 | [23 empty] | NO |  |  | INDUS | IN-1043179 |  |  | 1 |  | 0 |  | 0 |  | 0 |  | 0 |  | 1 |  | Material not found during in survey | Material not found during in survey | Pending |  | 73 | 16 | 0 | 0 | 0
AP | 2025-09-12 |  | MW-D-AP-12092025-9490 | NDL005/NDL027 | MW | From POP_Tree | NDL005-NDL027 | NDL027-NDL005 | NDL005 | XPIC | NA | 0 | NA | MODEM | Ericsson | Split |  | 15Ghz |  |  | AP_NDL005-NDL027_Ericsson_AMM 20P_Split_15Ghz¦AP¦NDL005-NDL027¦NDL005¦MODEM¦NA | AP_NDL005 | 900 | Vedangcellular | 2025-12-11 | 2025-11-17 | NA | 0 |  | INVALID | 0 | [23 empty] | NO |  |  | INDUS | IN-1043179 |  |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | Material not found during in survey | Material not found during in survey | Pending |  | 73 | 16 | 0 | 0 | 0
AP | 2025-09-12 |  | MW-D-AP-12092025-9490 | NDL005/NDL027 | MW | From POP_Tree | NDL005-NDL027 | NDL027-NDL005 | NDL027 | XPIC | NA | 0 | NA | MDU | Ericsson | Split |  | 15Ghz |  |  | AP_NDL005-NDL027_Ericsson_AMM 20P_Split_15Ghz¦AP¦NDL005-NDL027¦NDL027¦MDU¦NA | AP_NDL027 | 123 | Vedangcellular | 2025-12-11 | 2025-11-17 |  | 0 |  | INVALID | 0 | [23 empty] | NO |  |  | INDUS | IN-1273697 |  |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | Material not found during in survey | Material not found during in survey | Pending |  | 73 | 16 | 0 | 0 | 0
AP | 2025-09-12 |  | MW-D-AP-12092025-9490 | NDL005/NDL027 | MW | From POP_Tree | NDL005-NDL027 | NDL027-NDL005 | NDL027 | XPIC | 0.6 | 1 | NA7956 | ANTENNA | Ericsson | Split | NA | 15Ghz | 0.0.0.0 | NA | AP_NDL005-NDL027_Ericsson_AMM 20P_Split_15Ghz¦AP¦NDL005-NDL027¦NDL027¦ANTENNA¦NA7956 | AP_NDL027 | 123 | Vedangcellular | 2025-12-11 | 2025-11-17 | NA | 0 |  | INVALID | 0 | [23 empty] | NO |  |  | INDUS | IN-1273697 |  |  | 1 |  | 0 |  | 0 |  | 0 |  | 0 |  | 1 |  | Material not found during in survey | Material not found during in survey | Pending |  | 73 | 16 | 0 | 0 | 0
AP | 2025-09-12 |  | MW-D-AP-12092025-9490 | NDL005/NDL027 | MW | From POP_Tree | NDL005-NDL027 | NDL027-NDL005 | NDL027 | XPIC | 6363 | 1 | DL6A002742 | ODU | Ericsson | Split | AMM 6P | 15Ghz | 0.0.0.0 | RLT-1/5/1 | AP_NDL005-NDL027_Ericsson_AMM 20P_Split_15Ghz¦AP¦NDL005-NDL027¦NDL027¦ODU¦DL6A002742 | AP_NDL027 | 123 | Vedangcellular | 2025-12-11 | 2026-02-26 | NA | 0 |  | INVALID | 0 | [23 empty] | NO |  |  | INDUS | IN-1273697 |  |  | 1 |  | 0 |  | 0 |  | 0 |  | 0 |  | 1 |  | Material not found during in survey | Material not found during in survey | Pending |  | 73 | 16 | 0 | 0 | 0
AP | 2025-09-12 |  | MW-D-AP-12092025-9490 | NDL005/NDL027 | MW | From POP_Tree | NDL005-NDL027 | NDL027-NDL005 | NDL027 | XPIC | NA | 0 | NA | MODEM | Ericsson | Split |  | 15Ghz |  |  | AP_NDL005-NDL027_Ericsson_AMM 20P_Split_15Ghz¦AP¦NDL005-NDL027¦NDL027¦MODEM¦NA | AP_NDL027 |  | Vedangcellular | 2025-12-11 | 2025-11-17 | NA | 0 |  | INVALID | 0 | [23 empty] | NO |  |  | INDUS | IN-1273697 |  |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | Material not found during in survey | Material not found during in survey | Pending |  | 73 | 16 | 0 | 0 | 0
AP | 2025-09-12 |  | MW-D-AP-12092025-9490 | NDL005/NDL027 | MW | From POP_Tree | NDL005-NDL027 | NDL027-NDL005 | NDL027 | XPIC | NA | 0 | NA | IDU | Ericsson | Split |  | 15Ghz |  |  | AP_NDL005-NDL027_Ericsson_AMM 20P_Split_15Ghz¦AP¦NDL005-NDL027¦NDL027¦IDU¦NA | AP_NDL027 | 123 | Vedangcellular | 2025-12-11 | 2025-11-17 | NA | 0 |  | INVALID | 0 | [23 empty] | NO |  |  | INDUS | IN-1273697 |  |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | Material not found during in survey | Material not found during in survey | Pending |  | 73 | 16 | 0 | 0 | 0
AP | 2025-09-12 |  | MW-D-AP-12092025-9490 | NDL005/NDL027 | MW | From POP_Tree | NDL005-NDL027 | NDL027-NDL005 | NDL027 | XPIC | 6363 | 1 | CN32500946 | ODU | Ericsson | Split | AMM 6P | 15Ghz | 0.0.0.0 | RLT-1/4/1 | AP_NDL005-NDL027_Ericsson_AMM 20P_Split_15Ghz¦AP¦NDL005-NDL027¦NDL027¦ODU¦CN32500946 | AP_NDL027 | 123 | Vedangcellular | 2025-12-11 | 2025-11-17 |  | 0 |  | INVALID | 0 | [23 empty] | NO |  |  | INDUS | IN-1273697 |  |  | 1 |  | 0 |  | 0 |  | 0 |  | 0 |  | 1 |  | Material not found during in survey | Material not found during in survey | Pending |  | 73 | 16 | 0 | 0 | 0
AP | 2025-09-02 |  | MW-D-AP-02092025-1060 | BANU11/VMTA12 | MW | From POP_Tree | BANU11-VMTA12 | VMTA12-BANU11 | BANU11 | 1+0 | 6365 | 1 | CN35654883 | ODU | Ericsson | Full-outdoor | MINI-LINK 6366/4 | 15GHz | 0.0.0.0 | FRLT 1/1/1 | AP_BANU11-VMTA12_Ericsson_NA_Full-outdoor_15GHz¦AP¦BANU11-VMTA12¦BANU11¦ODU¦CN35654883 | AP_BANU11 | 151-MKL1-110444 | FrogCell | 2026-01-19 | 2025-10-30 | 6365 | 1 | CN35654883 |  | 1 | SREQ2594286 | 2025-10-30 | 2025-10-30 | 6365 | 1 | CN35654883 |  | 2025-11-01 | 5246561 | 2025-11-02 | 2025-11-02 | 2025-11-02 | INVA` | INVA` | INVA` | INVA` | INVA` | INVA` | INVA` | INVA` | INVA` | INVA` | INVA` | INVA` |  |  | INDUS | IN-1064921 |  | 34900398 | 0 | NA | 0 | NA | 0 | NA | 0 | NA | 0 | NA | 0 | NA | Submission Done | Submission Done | Done | SRN/CAM | 130 | 8 | 2 | 0 | 27 |  |  |  |  | SREQ
AP | 2025-09-02 |  | MW-D-AP-02092025-1060 | BANU11/VMTA12 | MW | From POP_Tree | BANU11-VMTA12 | VMTA12-BANU11 | BANU11 | 1+0 | NA | 0 | NA | IDU | Ericsson | Full-outdoor |  | 15GHz |  |  | AP_BANU11-VMTA12_Ericsson_NA_Full-outdoor_15GHz¦AP¦BANU11-VMTA12¦BANU11¦IDU¦NA | AP_BANU11 | 151-MKL1-110444 | FrogCell | 2026-01-19 | 2025-10-30 | NA | 0 |  |  | 0 | [23 empty] | NO |  |  | INDUS | IN-1064921 |  |  | 0 | NA | 0 | NA | 0 | NA | 0 | NA | 0 | NA | 0 | NA | Submission Done | Submission Done | Done |  | 130 | 8 | 2 | 0 | 27
AP | 2025-09-02 |  | MW-D-AP-02092025-1060 | BANU11/VMTA12 | MW | From POP_Tree | BANU11-VMTA12 | VMTA12-BANU11 | BANU11 | 1+0 | NA | 0 | NA | MODEM | Ericsson | Full-outdoor |  | 15GHz |  |  | AP_BANU11-VMTA12_Ericsson_NA_Full-outdoor_15GHz¦AP¦BANU11-VMTA12¦BANU11¦MODEM¦NA | AP_BANU11 | 151-MKL1-110444 | FrogCell | 2026-01-19 | 2025-10-30 | NA | 0 |  |  | 0 | [23 empty] | NO |  |  | INDUS | IN-1064921 |  |  | 0 | NA | 0 | NA | 0 | NA | 0 | NA | 0 | NA | 0 | NA | Submission Done | Submission Done | Done |  | 130 | 8 | 2 | 0 | 27
AP | 2025-09-02 |  | MW-D-AP-02092025-1060 | BANU11/VMTA12 | MW | From POP_Tree | BANU11-VMTA12 | VMTA12-BANU11 | BANU11 | 1+0 | 0.6 | 1 | NA | ANTENNA | Ericsson | Full-outdoor | NA | 15GHz | 0.0.0.0 | NA | AP_BANU11-VMTA12_Ericsson_NA_Full-outdoor_15GHz¦AP¦BANU11-VMTA12¦BANU11¦ANTENNA¦NA | AP_BANU11 | 151-MKL1-110444 | FrogCell | 2026-01-19 | 2025-10-30 | 0.6 | 1 | A00023710705 |  | 1 | INVALID | 2025-10-30 | 2025-10-30 | 0.6 | 1 | A00023710705 |  | 2025-11-01 | 5246561 | 2025-11-02 | 2025-11-02 | 2025-11-02 | 2025-11-02 | 1 | 2025-11-02 | Done | 2025-11-06 | 1 | 2025-11-06 | 1 | Ok | Complete | Processed | NO | 2025-02-11 | R/RL-7414594 | INDUS | IN-1064921 |  | 34900394 | 0 | NA | 0 | NA | 0 | NA | 0 | NA | 0 | NA | 0 | NA | Submission Done | Submission Done | Done | SRN/CAM | 130 | 8 | 2 | 0 | 27 |  |  |  |  | SREQ
AP | 2025-09-02 |  | MW-D-AP-02092025-1060 | BANU11/VMTA12 | MW | From POP_Tree | BANU11-VMTA12 | VMTA12-BANU11 | BANU11 | 1+0 | ML-6366 | 1 | CN39126372 | MDU | Ericsson | Full-outdoor | MINI-LINK 6366/4 | 15GHz | 0.0.0.0 | FRLT 1/1/1 | AP_BANU11-VMTA12_Ericsson_NA_Full-outdoor_15GHz¦AP¦BANU11-VMTA12¦BANU11¦MDU¦CN39126372 | AP_BANU11 | 151-MKL1-110444 | FrogCell | 2026-01-19 | 2025-10-30 | ML-6366 | 1 | CN39143499 |  | 1 |  |  | 2025-10-30 | ML-6366 | 1 | INVALD |  | INVALID |  | 2025-11-02 | 2025-11-02 | 2025-11-02 | 2025-11-02 | 1 | 2025-11-02 | Done | 2025-11-06 | 1 | 2025-11-06 | 1 | Ok | Complete | Processed | NO |  |  | INDUS | IN-1064921 |  | 34900397 | 0 | NA | 0 | NA | 0 | NA | 0 | NA | 0 | NA | 0 | NA | Submission Done | Submission Done | Done | SRN/CAM | 130 | 8 | 2 | 0 | 27
AP | 2025-09-02 |  | MW-D-AP-02092025-1060 | BANU11/VMTA12 | MW | From POP_Tree | BANU11-VMTA12 | VMTA12-BANU11 | VMTA12 | 1+0 | 6365 | 1 | CN39117279 | ODU | Ericsson | Full-outdoor | MINI-LINK 6366/4 | 15GHz | 0.0.0.0 | RLT-1/1/1 | AP_BANU11-VMTA12_Ericsson_NA_Full-outdoor_15GHz¦AP¦BANU11-VMTA12¦VMTA12¦ODU¦CN39117279 | AP_VMTA12 | 151-1577-27785196 | FrogCell | 2026-01-19 | 2025-10-30 | 6365 | 1 | CN39117279 |  | 1 | SREQ2594280 | INVALID | INVALID | 6365 | 1 | CN39117279 |  | 2025-11-01 | 5246558 | 2025-11-02 | INVALID | INVALID | INVALID | 1 | 2025-11-02 | Done | 2025-11-06 | 1 | 2025-11-06 | 1 | Ok | Complete | Processed | NO |  |  | INDUS | IN-3241567 |  | 34900399 | 0 | NA | 0 | NA | 0 | NA | 0 | NA | 0 | NA | 0 | NA | Submission Done | Submission Done | Done | SRN/CAM | 130 | 8 | 2 | 0 | 27 |  |  |  |  | INVALID
AP | 2025-09-02 |  | MW-D-AP-02092025-1060 | BANU11/VMTA12 | MW | From POP_Tree | BANU11-VMTA12 | VMTA12-BANU11 | VMTA12 | 1+0 | 0.6 | 1 | NA | ANTENNA | Ericsson | Full-outdoor | NA | 15GHz | 0.0.0.0 | NA | AP_BANU11-VMTA12_Ericsson_NA_Full-outdoor_15GHz¦AP¦BANU11-VMTA12¦VMTA12¦ANTENNA¦NA | AP_VMTA12 | 151-1577-27785196 | FrogCell | 2026-01-19 | 2025-10-30 | 0.6 | 1 | A000A000900 |  | 1 | SREQ2594280 | 2025-10-30 | 2025-10-30 | INVALID | 1 |  |  | 2025-11-01 | 5246558 | 2025-11-02 | 2025-11-02 | 2025-11-02 | 2025-11-02 | 1 | 2025-11-02 | Done | 2025-11-06 | 1 | 2025-11-06 | 1 | Ok | Complete | Processed | NO | 2026-02-04 | R/RL-8261698 | INDUS | IN-3241567 |  | 34900395 | 0 | NA | 0 | NA | 0 | NA | 0 | NA | 0 | NA | 0 | NA | Submission Done | Submission Done | Done | SRN/CAM | 130 | 8 | 2 | 0 | 27 |  |  |  |  | REQ
AP | 2025-09-02 |  | MW-D-AP-02092025-1060 | BANU11/VMTA12 | MW | From POP_Tree | BANU11-VMTA12 | VMTA12-BANU11 | VMTA12 | 1+0 | NA | 0 | NA | MODEM | Ericsson | Full-outdoor |  | 15GHz |  |  | AP_BANU11-VMTA12_Ericsson_NA_Full-outdoor_15GHz¦AP¦BANU11-VMTA12¦VMTA12¦MODEM¦NA | AP_VMTA12 | 151-1577-27785196 | FrogCell | 2026-01-19 | 2025-10-30 | NA | 0 |  |  | 0 | [23 empty] | NO |  |  | INDUS | IN-3241567 |  |  | 0 | NA | 0 | NA | 0 | NA | 0 | NA | 0 | NA | 0 | NA | Submission Done | Submission Done | Done |  | 130 | 8 | 2 | 0 | 27
AP | 2025-09-02 |  | MW-D-AP-02092025-1060 | BANU11/VMTA12 | MW | From POP_Tree | BANU11-VMTA12 | VMTA12-BANU11 | VMTA12 | 1+0 | ML-6366 | 1 | CN39124057 | MDU | Ericsson | Full-outdoor | MINI-LINK 6366/4 | 15GHz | 0.0.0.0 | RLT-1/1/1 | AP_BANU11-VMTA12_Ericsson_NA_Full-outdoor_15GHz¦AP¦BANU11-VMTA12¦VMTA12¦MDU¦CN39124057 | AP_VMTA12 | 151-1577-27785196 | FrogCell | 2026-01-19 | 2025-10-30 | ML-6366 | 1 | CN39143501 |  | 1 | SREQ2594280 | 2025-10-30 | 2025-10-30 | ML-6366 | 1 | CN39143501 |  | 2025-11-01 | 5246558 |  | 2025-11-02 | 2025-11-02 | 2025-11-02 | 1 | 2025-11-02 | Done | 2025-11-06 | 1 | 2025-11-06 | 1 | Ok | Complete | Processed | NO |  |  | INDUS | IN-3241567 |  | 34900396 | 0 | NA | 0 | NA | 0 | NA | 0 | NA | 0 | NA | 0 | NA | Submission Done | Submission Done | Done | SRN/CAM | 130 | 8 | 2 | 0 | 27 |  |  |  |  | CREQ
AP | 2025-09-02 |  | MW-D-AP-02092025-1060 | BANU11/VMTA12 | MW | From POP_Tree | BANU11-VMTA12 | VMTA12-BANU11 | VMTA12 | 1+0 | NA | 0 | NA | IDU | Ericsson | Full-outdoor |  | 15GHz |  |  | AP_BANU11-VMTA12_Ericsson_NA_Full-outdoor_15GHz¦AP¦BANU11-VMTA12¦VMTA12¦IDU¦NA | AP_VMTA12 | 151-1577-27785196 | FrogCell | 2026-01-19 | 2025-10-30 | NA | 0 |  |  | 0 | [23 empty] | NO |  |  | INDUS | IN-3241567 |  |  | 0 | NA | 0 | NA | 0 | NA | 0 | NA | 0 | NA | 0 | NA | Submission Done | Submission Done | Done |  | 130 | 8 | 2 | 0 | 27

## LB Report
Circle | Nominal Aop | Nominal Quarter | Plan Id | Plan Release Date | Ageing | Ageing Range | Plan category(New Deployment hybrid/FO/New Deployment XPIC/MIMO Upgrade/Existing 1+0 to XPIC Upgrade/Capacity Upgrade soft/DC/1+0 to 1 Gig Upgrade/Dual XPIC Upgrade/E Band/Frequency Change/Card Upgrade) | Final Project | Plan status ( Deployment done / Deployment Pending ) | Deployment Date/Month | Equipment Make | Hop Nomenclature Site-A | Hop Nomenclature Site-B | Link ID | Channel | Polarization | Site ID-A | Site A Lat | Site A Long | Tx Site Elevation (m) | BER10e6 Tx Power (dBm) | Tx Frequency (MHz) | BER10e6 Rx Level (dBm) | Tx Ant. Azimuth (°) | Tx Ant. Height (m) | Tx Antenna | Tx Ant. Gain (dB) | BER10e6 EIRP (dBm) | Site ID -B | Site B Lat | Site B Long | Rx Site Elevation (m) | Rx Frequency (MHz) | Rx Ant. Azimuth (°) | Rx Ant. Height (m) | Rx Antenna | Rx Ant. Gain (dB) | Tx Radio | Distance (km) | Bandwidth (MHz) | BER10e6 Eff. Margin (dB) | BER10e6 Rain Interference Thr. Deg. (dB) | BER10e6 Total Perf. Year (Unav. %) | Availability | ACM Status | ACM Min QAM | ACM Max QAM | ATPC Status | (MODEM(IF Card)/Ethernet Port) Site-A | (MW Chasis/CSR (CEN/EPT/NPT/BBU) Site-A | (MODEM(IF Card)/Ethernet Port) Site-B | (MW Chasis/CSR (CEN/EPT/NPT/BBU) Site-B | Hop Dismantle Y / N | Dismantle Hop ID | Dismantle Hop Type | Dismantle Hop Modem A | Dismantle Hop Chassis A | Antenna Size Site-A | Dismantle Hop Modem B | Dismantle Hop Chassis B | Antenna Size Site-B | PCM PATH | Fiber POP Id | Remarks | Junoon.2.0 LB (Yes/No) | Assigned To | Assigned To Department | Task Status | Cancellation Reason | Last Updated Date | AT Completed Date | TS Completed Date | Hop Type | Modulation | DCN RA Number | DCN VLAN | GATEWAY IP | Site A End IP | Site B End IP | Antenna Beam Width
ROTN | FY24_25 | Q3 | MW-N-ROTN-14122024-599 | 2024-12-14 | 373 | > 180 days | NEW DEPLOYMENT XPIC | NETWORK RE-ENGINEERING | ACCEPTANCE TEST | 2025-12-05 | HUAWEI | KNKCI4 | SLM367 | KNKCI4-SLM367 | TN_15G_56M_F6F7 | H+V | KNKCI4 | 11.6971 | 78.1754 | 304.7 | 10 | 15089 | -33.11 | 313.7 | 30 | 0.6 | 36.799999999999997 | 46.8 | SLM367 | 11.7038 | 78.1682 | 316 | 14669 | 133.7 | 30 | 0.6 | 36.799999999999997 | 15GXMC32048Q56MX | 1.08 | 56 | 23.9 | 0.0 |  | 99.9998 | Enable | QPSK | 2048QAM | Disable | ISM6 | OPTIX RTN 910 | ISM6 | OPTIX RTN 910 | N | [8 empty] | KNKCI4¦SLM367 | KNKCI4 |  |  | Vedangcellular-Siva-A1Z6SKAO | Circle I&C Partner | ASSIGNED |  | 2024-12-17 |  |  | XPIC+DC |  | 528647 | 1474 | 2401:4900:c4:40ec:0:107:0:101/120 | 2401:4900:c4:40ec:0:107:0:170 | 2401:4900:c4:40ec:0:107:0:171 | 2.5