## Revision
Circle | Plan ID | Change Plan Status | LB Revision Status | Remarks
JK |  | Revise | Yes | Revision
JK | INVALID | Revise | Yes | Revision
JK | MW-N-JK-16062023-10369 |  | Yes | Revision
JK | MW-N-JK-16062023-10369 | INVALID | Yes | Revision
JK | MW-N-JK-16062023-10369 | Revise |  | Revision
JK | MW-N-JK-16062023-10369 | Revise | INVALID | Revision
JK | MW-N-JK-08082023-39347 | Revise | No | not assigned
JK | MW-N-JK-22012025-9764 | Revise | No | SR-RAFI
JK | MW-N-JK-03082023-37986 | Revise | N0 | duplicate plans
JK | MW-N-JK-03082023-37986 | Revise | No | duplicate plans

## LB
Circle | Nominal Aop | Nominal Quarter | Plan Id | Plan Release Date | Ageing | Ageing Range | Plan category(New Deployment hybrid/FO/New Deployment XPIC/MIMO Upgrade/Existing 1+0 to XPIC Upgrade/Capacity Upgrade soft/DC/1+0 to 1 Gig Upgrade/Dual XPIC Upgrade/E Band/Frequency Change/Card Upgrade) | Final Project | Plan status ( Deployment done / Deployment Pending ) | Plan Stage | Deployment Date/Month | Equipment Make | Hop Nomenclature Site-A | Hop Nomenclature Site-B | Link ID | Channel | Polarization | Site ID-A | Site A Lat | Site A Long | Tx Site Elevation (m) | BER10e6 Tx Power (dBm) | Tx Frequency (MHz) | BER10e6 Rx Level (dBm) | Tx Ant. Azimuth (°) | Tx Ant. Height (m) | Tx Antenna | Tx Ant. Gain (dB) | BER10e6 EIRP (dBm) | Site ID -B | Site B Lat | Site B Long | Rx Site Elevation (m) | Rx Frequency (MHz) | Rx Ant. Azimuth (°) | Rx Ant. Height (m) | Rx Antenna | Rx Ant. Gain (dB) | Tx Radio | Distance (km) | Bandwidth (MHz) | BER10e6 Eff. Margin (dB) | BER10e6 Rain Interference Thr. Deg. (dB) | Availability | ACM Status | ACM Min QAM | ACM Max QAM | Radio Code A | Radio Code B | Modem Code Site-A | MDU Code Site-A | Chassis Code Site-A | Antenna Code Site-A | Modem Code Site-B | MDU Code Site-B | Chassis Code Site-B | Antenna Code Site-B | ATPC Status | ATPC MIN | ATPC MAX | (MODEM(IF Card)/Ethernet Port) Site-A | (MW Chasis/CSR (CEN/EPT/NPT/BBU) Site-A | MW Chasis New or Existing Site-A | Free Slot/Port Interface Detail Site A | (MODEM(IF Card)/Ethernet Port) Site-B | (MW Chasis/CSR (CEN/EPT/NPT/BBU) Site-B | MW Chasis New or Existing Site-B | Free Slot/Port Interface Detail Site B | Hop Dismantle Y / N | Dismantle Hop ID | Dismantle Hop Type | Dismantle Hop Modem A | Dismantle Hop Chassis A | Antenna Size Site-A | Dismantle Hop Modem B | Dismantle Hop Chassis B | Antenna Size Site-B | PCM PATH | Fiber POP Id | Remarks | Assigned To | Assigned To Department | Task Status | Cancellation Reason | Last Updated Date | AT Completed Date | TS Completed Date | Hop Type | DCN RA Number | DCN RA Status | DCN VLAN | GATEWAY IP | Site A End IP | Site B End IP | Antenna Beam Width | Node ID Site A | Node ID Site B | MO Number Site A | MO Number Site B | For Site ID | MRMC Script ID | TS Plan Released Status | TS Plan ID
JK | FY23_24 | Q1 | MW-N-JK-16062023-10369 | 2023-06-14 | 1100 | > 180 days | NEW DEPLOYMENT HYBRID/FO | RELOCATION | Plan Cancellation | Request For Cancellation | 2023-04-27 | HUAWEI | AKR719 | KHN920 | AKR719-KHN920 | JK_15G_28M_F13 | H | AKR719 | 33.7734 | 75.1962 | 1637.4 | 13 | 14851 | -33.1 | 115.36 | 35 | 0.3 | 30.9 | 17.64 | KHN920 | 33.7707 | 75.21 | 1644.16 | 15271 | 295.36 | 50 | 0.3 | 30.9 | 15GXMC21024Q28M | 1.31 | 28 | 30.47 | 2.0299999999999998 | 100 | Enable | QPSK | 1024QAM | [10 empty] | Disable | NA | NA | ISV3 | OPTIX RTN 910 |  |  | ISV3 | OPTIX RTN 910 |  |  | n | N | NR | NR | NR | NR | NR | NR | NR | SRR129¦AKR719¦KHN920 | SRR129 |  | Airtel-Neeraj-B0282121 | Circle MW Planner | ACCEPTANCE TEST | Others | 2025-02-10 |  |  | 1+0 | NR | [8 empty] | 23584914 | 23584916 | KHN920 | NA
JK | FY23_24 | Q2 | MW-N-JK-08082023-39347 | 2023-08-08 | 1045 | > 180 days | NEW DEPLOYMENT HYBRID/FO | RELOCATION | Plan Cancellation | Request For Cancellation |  | HUAWEI | SMB473 | SMB943 | SMB473-SMB943 | JK_15G_56M_F12F13 | V | SMB473 | 32.5577 | 75.1283 | 406.6 | 12 | 14837 | -30.48 | 113 | 40 | 0.3 | 30.9 | 48.8 | SMB943 | 32.554 | 75.1383 | 434.9 | 15257 | 293.5 | 38 | 0.3 | 30.9 | 15GXMC21024Q28M | 1.03 | 56 | 25.0 | 0.2 | 99.9998 | Enable | QPSK | 1024QAM | 44 | 43 | 39 | NA | NA | 451 | 39 | NA | NA | 451 | Disable | NA | NA | ISM6 | RTN910II |  |  | ISM6 | RTN910II |  |  | N | N | NR | NR | NR | NR | NR | NR | NR | SMB473¦SMB943 | SMB473 |  | Airtel-Neeraj-B0282121 | Circle MW Planner | SR-RFAI |  | 2025-07-11 |  |  | 1+0 DC | NR |  | NA | NA | 2401:4900:18:434:0:4e5:0:141 | 2401:4900:18:434:0:4e5:0:142 | [5 empty] | SMB943 | NA
JK | FY23_24 | Q2 | MW-N-JK-26072023-35561 | 2023-07-20 | 1064 | > 180 days | NEW DEPLOYMENT HYBRID/FO | JUNOON 2 | Plan Cancellation | Request For Cancellation | 2023-08-21 | HUAWEI | RAJ921 | RAJ113 | RAJ921-RAJ113 | 15_3 GHz_56MHz_15_3 GHz_56MHz | V | RAJ921 | 33.3714 | 74.2942 | 978.68 | 11 | 15257 | -32.58 | 32.79 | 40 | 0.3 | 36.8 | 47.8 | RAJ113 | 33.38 | 74.3007 | 961.23 | 14837 | 212.79 | 50 | 0.3 | 36.8 | 15GXMC31024Q56M | 1.13 | 56 | 26.92 | 0.43 | 99.99986994 | 1024QAM | Enable | 128QAM | [10 empty] | 1024QAM | NA | NA | Disabled | ISV3 |  |  | RTN910 | ISV3 |  |  | RTN910 | N | NR | NR | NR | NR | NR | NR | NR | RAJ452¦RAJ921¦RAJ113 | RAJ452 | y | Airtel-Neeraj-B0282121 | Circle MW Planner | SR-RFAI |  | 2025-12-05 | 2023-07-17 |  | 1+0 DC | NR | [10 empty] | RAJ113 | NA